## User Story
Issue Type | Summary | Priority
Epic 1 | Resources Functionality | High
Story 1 | As a Learner,I want to Click On Resources | High
Sub Story1 | As a Learner, I want to access AI-related blogs so that I can stay updated with trends and tutorials.
Sub Story2 | As a Learner,I want to select the which course blog I need
Sub Story3 | As a Learner,I want to choose the last updated Blog
Sub Story4 | As a Learner,I want to Click On webinars

## Test Scenarios
TestScenarioID | Requirement ID | Test Scenario Description | Type of Testing | Possible No. of TestCases | Test Case Details
TS_Website_01 | REQ_Website_01 | Verification of working of website in all kinds of browser. | Functional Testing | 3 | 1. To validate that when website url is entered in the browser it opens the website. 2. To validate that website is displyed correctly in all the browsers. 3. To validate that user is able to perform the tasks on website in all kinds of browsers.
TS_Edureka_HomePage_01 | REQ_Edureka_HomePage_01 | To Verify Resources Functionality | Functional Testing | 5 | 1.To validate Resources Functionality,click on Resources 2.To Validate the functionality,Click on blogs 3.To validate the blogs functionality,select the course which User wants a blog 4.To validate the blogs functionality,User wants a blog which the course is not present 5.To Validate the blogs functionality,click on the course which User needs a blog then start learning.

## Test Cases
Test Case ID | Test Scenario | Precondition | Test Condition | Test Case Steps |  | Expected Result | Actual Result Iteration 1 | Status Iteration 1 | Actual Result Iteration 2 (to be updated only if test case failed in Iteration 1) | Status Iteration 2 (to be updated only if test case failed in Iteration 1) | Comments | Req: Reference
<Sequence number>z | <Identify test scenarios> | <This cell specifies the state a system and its environment must be in before this specific test case can be run> | <This cell describes what to test for i.e. the condition which is being tested for> | <This cell describes how to test i.e. the detailed testing procedure> | <Mention test data to be used> | <Describe the expected test result> | <Describe the actual test result after execution of test cases. In case screenshots need to be attached to substantiate the test result, use the references tab.> | Status of the test case whether it got passed/ failed/Hold in interation 1. | <Describe the actual test result after execution of test cases second time. In case screenshots need to be attached to substantiate the test result, use the references tab.> | New status of test case after it failed in Iteration 1.
TC_Edureka_HomePage_01 | TS_Edureka_HomePage_01 | User is on homepage | Validate Resources button functionality | 1. Locate and click on Resources | N/A | Resources section should open | Opened resources section | Passed
TC_Edureka_HomePage_02 | TS_Edureka_HomePage_01 | Resources section open | Validate Blogs option functionality | 1. Click on Blogs under Resources | N/A | Blogs page should open | opened Blogs Page | Passed
TC_Edureka_HomePage_03 | TS_Edureka_HomePage_01 | Blogs page open | Validate course-specific blog selection | 1. Select course from dropdown 2. Click on blog | Course = “AI” | Blog related to selected course should open | Opened the blog related to the selected course | Passed
TC_Edureka_HomePage_04 | TS_Edureka_HomePage_01 | Blogs page open | Validate behavior for unavailable course | 1. Search for a course not listed | Course = “Quantum Computing” | Message “No blog available” should appear | Didn't get any message | Failed
TC_Edureka_HomePage_05 | TS_Edureka_HomePage_01 | Blog available | Validate Start Learning functionality | 1. Click on blog 2. Click “Start Learning” | Selected blog | Blog content should open and learning begins | Blog contenet Opened | Passed

## Defect Report
Defect Id. | Module name | Defect Summary | Defect Priority | Assigned To | Status

## RTM
BR_ID | TR_ID | TS_ID | TC_ID | STATUS | DR_ID

## Summary
TEST EXECUTION SUMMARY
Project Name | Module Name | Total Cases | Total Passed | Total Failed | Total Executed | Pass Percentage | Fail Percentage | Complition Percentage