## AUT_Participants_Models
Batch: | V & V Testing Banglore Aug 26th
Sprint Date: | 6th Nov 2025 - 18th Nov 2025
Application Under Test: | Edureka
S.No | Associates Name | Module undet test | BR_ID
1 | Katikireddy Shirisha | Careers | BR_Edureka_Careers_01
2 | aedunuri Manasa | serach | BR_Edureka_Careers_02
3 | Baisegowni Reddy Tejasree | Resources | BR_Edureka_Careers_03
4 | Precharla Divya Sai | Discover_Top_Categories | BR_Edureka_Careers_04
5 | murarishetty vyshnavi | Trending_Courses | BR_Edureka_Careers_05
Group Leader: | Katikireddy Shirisha

## User Stories
Application Under Test: | Edureka
Module: | Careers Page
Epic | User story Id | User Story | Acceptance criteria
Epic_ Edureka_Careers_01 | US_ID_Edureka_Careers_01 | As a learner, I want to explore and apply for job opportunities so that I can join Edureka. | 1.The user should be able to view Open Positions. 2.It should return relevant job postings and Internship Listings . 3.The user should be able to Read Job Descriptions. 4.Users should be able to fill form and submimt applications.
| US_ID_Edureka_Careers_02 | As a learner, I want to explore Corporate Training options and connect with Edureka for services. | 1.The user should be able to access Corporate Training section. 2.The user should be able to Fill Advisor Form. 3.The user should be able to Download course list after form submission.

## Test Scenarios
Application Under Test: |  |  | Edureka
Test Scenario
S.No | Module | Test Requirement Id | Test Scenario Id | Test Scenario Description
1 | Careers | TR_Edureka_careers_01 | TS_Edureka_Careers_01 | To verify Careers Functionality
2 |  |  | TS_Edureka_Careers_02 | To verify Internship Application Form Functionality
3 |  |  | TS_Edureka_Careers_03 | To verify Corporate Training Functionality
4 |  |  | TS_Edureka_Careers_04 | To verify Download Full Course List Functionality

## Test Case Design
| Application Under Test: | Edureka
TS_ID | TC_ID | Objective | Pre condition | Steps | Test Data | Expected Result | Post condition | Test Type | Actual Result | Status
TS_Edureka_Careers_01 | TC_Edureka_Careers_01 | Validate navigation to Careers page from footer. | Edureka application is displayed on screen | 1.Scroll down to the foorter. 2.Click on Careers. | N/A | It should land to "Join Us" page. | Page loaded | Functional Testing | It lands to "Join Us" Page | Passed
| TC_Edureka_Careers_02 | Validate visibility of open positions section. | "Join Us" Page is displayed on screen. | 1.Scroll down to find OPEN POSITIONS. | N/A | It should show "OPEN POSITIONS" section | Section visible | Functional Testing | It shows "OPEN POSITIONS" section | Passed
| TC_Edureka_Careers_03 | Validate job detail page for Internship - Research Analyst | "OPEN POSITIONS" section is displayed on screen. | 1.Click on "Internship - Research Analyst" under marketing. | N/A | It should open a new tab containing "Internship-Research Analyst" Job details | New tab opens | Functional Testing | It does opens a new tab containing "Internship-Research Analyst" Job details | Passed
| TC_Edureka_Careers_04 | Validate form submission with invalid email | A new tab with Job Details is displayed . | 1.Scroll down to find Job Details | N/A | Job details should be visible. | Jobs details available. | Functional Testing | Job details are visible. | Passed
TS_Edureka_careers_02 | TC_Edureka_Careers_05 | Validate visibility of "Apply Now" form | Job details Section is Displayed on screen. | 1.Scroll up from Job Details Section. 2.Find "Apply Now" Form in the right section of Job Details Page. | N/A | "Apply Now" Form should be visible. | Form visible | Functional Testing | "Apply Now" Form is visible. | Passed
| TC_Edureka_Careers_06 | Validate form submission with missing name | "Apply Now" Form is displayed on screen. | 1.Leave Name field as Empty in the form. 2.Enter valid Email. 3.Enter valid Mobile Number. 4.Attach valid Document. 5.Click on "SUBMIT APPLICATION". | 2.iris@gmail.com 3.1234567890 4.resume.txt | It should show an Error Message. | Error shown | Negative Testing | It shows an Error Message as "Please Provide valid name" | Passed
| TC_Edureka_Careers_07 | Validate form submission with invalid email | "Apply Now" Form is displayed on screen. | 1.Enter valid Name. 2.Enter Invalid Email. 3.Enter valid Mobile Number. 4.Attach valid Document. 5.Click on "SUBMIT APPLICATION". | 1.iris 2.iris@g.com 3.1234567890 4.resume.txt | It should show an Error Message. | Error expected | Negative Testing | No Error Shown. | Failed
| TC_Edureka_Careers_08 | Validate form submission with invalid mobile number | "Apply Now" Form is displayed on screen. | 1.Enter valid Name. 2.Enter valid Email. 3.Enter Invaild Mobile Number. 4.Attach valid Document. 5.Click on "SUBMIT APPLICATION". | 1.iris 2.iris@gmail.com 3.123dfg567890 4.resume.txt | It should show an Error Message. | Error shown | Negative Testing | It shows an Error Message as "Please Provide valid mobile no". | Passed
| TC_Edureka_Careers_09 | Validate form submission with unsupported resume format | "Apply Now" Form is displayed on screen. | 1.Enter valid Name. 2.Enter valid Email. 3.Enter vaild Mobile Number. 4.Attach unsupported file formatted Document. 5.Click on "SUBMIT APPLICATION". | 1.iris 2.iris@gmail.com 3.1234567890 4.resume.jpeg | form shouldn't submit. | Blocked | Negative Testing | form doesn't submit. | Passed
| TC_Edureka_Careers_10 | Validate form submission with valid data | "Apply Now" Form is displayed on screen. | 1,Enter valid Name. 2.Enter valid Email. 3.Enter valid Mobile Number. 4.Attach valid Document. 5.Click on "SUBMIT APPLICATION". | 1.iris 2.iris@gmail.com 3.1234567890 4.resume.png | A THANK YOU section should appear. | Success | Positive Testing | A THANK YOU section is appeared. | Passed+K12:K13
TS_Edureka_Careers_03 | TC_Edureka_Careers_11 | To validate Corporate Training visbility. | A 'Thank You' section is displayed next to the job details. | 1.Go to header section in . 2.Find Corporate Trianing tab. | N/A | Corporate Training tab should be Visible. | Tab visible | Functional Testing | Corporate Training tab is visbile. | Passed
TS_Edureka_Careers_04 | TC_Edureka_Careers_12 | To validate Download Full Course List button . | Corporate Training tab is displayed | 1.Scroll down. 2.Click on "Download Full Course List" under Curriculums,curated by industry leaders section. | N/A | It should display a form. | Form visible | Functional Testing | It displays a form. | Passed
| TC_Edureka_Careers_13 | To validate form submission with missing name. | A Form is displayed on screen. | 1.Leave Name field as Empty in the form. 2.Enter valid Company Name. 3.Enter valid Training Need form the dropdown. 4.Enter valid Email ID. 5.Enter valid Phone Number. 5.Click on "Download Full Course List". | 2.Capgemini 3.For Corporate 4.iris@gmail.com 5.1234567890 | It should show an Error Message. | Error shown | Negative Testing | It shows an Error Message as "Please enter your name". | Passed
| TC_Edureka_Careers_14 | To validate form submission with missing company name. | A Form is displayed on screen. | 1.Enter valid Name. 2.Leave Company Name field as Empty in the form. 3.Enter valid Training Need form the dropdown. 4.Enter valid Email ID. 5.Enter valid Phone Number. 5.Click on "Download Full Course List". | 1.iris 3.For Myself 4.iris@gmail.com 5.1234567890 | It should show an Error Message | Error shown | Negative Testing | It shows an Error Message as "Please enter your Company Name". | Passed
| TC_Edureka_Careers_15 | To validate form submission with invalid email format. | A Form is displayed on screen. | 1.Enter valid Name. 2.Enter valid Company Name. 3.Enter valid Training Need form the dropdown. 4.Enter Invalid Email ID. 5.Enter valid Phone Number. 5.Click on "Download Full Course List". | 1.iris 2.Capgemini 3.For Myself 4.iris@ 5.1234567890 | It should show an Error Message. | Error shown | Functional Testing | It shows an Error Message as "Please enter a valid email ID" | Passed
| TC_Edureka_Careers_16 | To validate form submission with invalid mobile number. | A Form is displayed on screen. | 1.Enter valid Name. 2.Enter valid Company Name. 3.Enter valid Training Need form the dropdown. 4.Enter valid Email ID. 5.Enter Invalid Phone Number. 5.Click on "Download Full Course List". | 1.iris 2.Capgemini 3.For Myself 4.iris@gmail.com 5.1123shyuhjko | It should show an Error Message. | Error shown | Negative Testing | It shows an Error Message as "Please enter a valid mobile number". | Passed
| TC_Edureka_Careers_17 | To validate form submission with valid data. | A Form is displayed on screen. | 1.Enter valid Name. 2.Enter valid Company Name. 3.Enter valid Training Need form the dropdown. 4.Enter valid Email ID. 5.Enter valid Phone Number. 5.Click on "Download Full Course List". | 1.iris 2.capgemini 3.For Myself 4.iris@gmail.com 5.1234567890 | A THANK YOU section should appear,and the file should download. | Success | Positive Testing | A THANK YOU section should appeared, and file is downloaded. | Passed
| TC_Edureka_Careers_18 | To validate confirmation message after submission. | A Thank You Section is displayed on screen. | 1.Close the Thank You Section by clicking on "X". | N/A | It should go back to Download Full Course List section. | Redirected | Functional Testing | It is going back to Download Full Course List section. | Passed

## Test Execution Summary Report
Test Execution Summary
S.No | Project Name | Test Scenario | Total Test Cases | Total Test Cases Executed | Total Test Cases Passed | Total Test Cases Failed | Pass Percentage | Fail Percentage | Completion Percentage
|  | Careers | 18 | 18 | 17 | 1 | 94.44% | 5.56% | 100%
1 | Edureka | To verify Careers Functionality | 4 | 4 | 4 | 0 | 100% | 0% | 100%
2 | Edureka | To verify Internship Application Form Functionality | 6 | 6 | 5 | 1 | 83.33% | 16.67% | 100%
3 | Edureka | To verify Corporate Training Functionality | 1 | 1 | 1 | 0 | 100% | 0% | 100%
4 | Edureka | To verify Download Full Course List Functionality | 7 | 7 | 7 | 0 | 100% | 0% | 100%

## RTM
Application Under Test: Edureka
Requirement Traceability Matrix
BR_ID | TR_ID | TS_ID | TC_ID | Status | Defect_Id
BR_Edureka_Careers_01 | TR_Edureka_Careers_01 | TS_Edureka_Careers_01 | TC_Edureka_Careers_01 | Passed
|  |  | TC_Edureka_Careers_02 | Passed
|  |  | TC_Edureka_Careers_03 | Passed
|  |  | TC_Edureka_Careers_04 | Passed
|  | TS_Edureka_Careers_02 | TC_Edureka_Careers_05 | Passed
|  |  | TC_Edureka_Careers_06 | Passed
|  |  | TC_Edureka_Careers_07 | Failed | DI_Edureka_Careers_01
|  |  | TC_Edureka_Careers_08 | Passed
|  |  | TC_Edureka_Careers_09 | Passed
|  |  | TC_Edureka_Careers_10 | Passed
|  | TS_Edureka_Careers_03 | TC_Edureka_Careers_11 | Passed
|  | TC_Edureka_Careers_04 | TC_Edureka_Careers_12 | Passed
|  |  | TC_Edureka_Careers_13 | Passed
|  |  | TC_Edureka_Careers_14 | Passed
|  |  | TC_Edureka_Careers_15 | Passed
|  |  | TC_Edureka_Careers_16 | Passed
|  |  | TC_Edureka_Careers_17 | Passed
|  |  | TC_Edureka_Careers_18 | Passed

## Defect Report
Defect Report
DefectId | Summary | Description | Steps to reproduce | Expected Behavior | Actual Behavior | Priority | Severity
DI_Edureka_Careers_01 | No error message displayed for invalid email input | Internship application form fails to validate incorrect email format, allowing submission without triggering an error message. | 1. Navigate to Careers , Internship ,Apply Now. 2. Enter valid name. 3. Enter invalid email (e.g., iris@g.com). 4. Fill other fields. 5. Submit | System should display error message for invalid email | No error message displayed; form accepted submission | High | Major

## Summary Report to stakehold
Test Summary Report format
1.Test Objective: | This document captures the various activities performed as part of testing the ‘Edureka Careers’ module, including Careers navigation, Internship application, Corporate Training access, and Course List download functionality.This document captures the various activities performed as part of Testing the ‘LinkedIn Jobs’ section.
2.Application Overview : | The Edureka Careers module provides learners with a platform to explore job opportunities, submit internship applications, and connect with Edureka for corporate training services. It facilitates both individual and enterprise engagement through structured forms and listings.
3.Testing Scope:
In-Scope: | Testing for the following are in scope:
1.Careers Page Navigation
2.Job Listings and Descriptions
3.Internship Application Form
4.Corporate Training Tab
5.Course List Download Form
6.Form Validations (Positive & Negative)
7.Confirmation Messages and Redirection
Out of Scope: | Admin-side job posting workflows
Areas not covered: | Following areas are not covered:
1.Resume storage and retrieval
2.Analytics tracking for job views
3.Email notification workflows
4.Accessibility Testing
5.Mobile responsiveness
6.Integration with external job boards
4.Test Metrices:
Total number of test cases planned: | 18
Total number of Test cases Executed: | 18
Total number of Test cases Passed: | 17
Total number of Test cases Failed: | 1
Total number of Test cases Planned | Total number of Test cases Executed | Total number of Test cases Passed | Total number of Test cases Failed | Remark
18 | 18 | 17 | 1
Graphical representation:
Requirement Traceability Matrix
BR_ID | TR_ID | TS_ID | TC_ID | Status | Defect_Id
BR_Edureka_Careers_01 | TR_Edureka_Careers_01 | TS_Edureka_Careers_01 | TC_Edureka_Careers_01 | Passed
|  |  | TC_Edureka_Careers_02 | Passed
|  |  | TC_Edureka_Careers_03 | Passed
|  |  | TC_Edureka_Careers_04 | Passed
|  | TS_Edureka_Careers_02 | TC_Edureka_Careers_05 | Passed
|  |  | TC_Edureka_Careers_06 | Passed
|  |  | TC_Edureka_Careers_07 | Failed | DI_Edureka_Careers_01
|  |  | TC_Edureka_Careers_08 | Passed
|  |  | TC_Edureka_Careers_09 | Passed
|  |  | TC_Edureka_Careers_10 | Passed
|  | TS_Edureka_Careers_03 | TC_Edureka_Careers_11 | Passed
|  | TC_Edureka_Careers_04 | TC_Edureka_Careers_12 | Passed
|  |  | TC_Edureka_Careers_13 | Passed
|  |  | TC_Edureka_Careers_14 | Passed
|  |  | TC_Edureka_Careers_15 | Passed
|  |  | TC_Edureka_Careers_16 | Passed
|  |  | TC_Edureka_Careers_17 | Passed
|  |  | TC_Edureka_Careers_18 | Passed
5.Types of testing performed
Functionality Testing | Functional testing is a type of software testing that verifies that a system or application functions correctly according to its specifications or requirements. This type of testing focuses on testing the functionality of the software and ensuring that it behaves as expected from the end user's perspective.
Positive Testing | Positive testing is a type of software testing that verifies the system behaves as expected when given valid and expected input.
Negative Testing | Negative testing is a type of software testing that checks how the system handles invalid, unexpected, or incorrect input.
6.Test Environment and Tools Used:
Application URL | https://www.edureka.co
Database | N/A
Tools Used | MS Excel
7.Recommendations and Suggestions: | Encourage users to provide feedback through surveys, polls, to continuously iterate and enhance the Edureka experience.
8.Exit Criteria: | 1. All the test cases that were planned are executed successfully.
2.No critical defects impacting the core functionality of the website.
3. All the identified issues are documented with clear steps to reproduce and resolve.
9.Sign Off: | Considering the nature of the identified defects as low severity and the completion of all planned test cases, the testing team recommends procedding with the release of the "Careers" module. Further enhancements and defects resolution can be scheduled for subsequent releases.