## AUT_participants_modules
Batch: | V & V
Sprint Date:
Application Under Test: | LinkedIn
S.No | Associates Name | Module undet test | BR_ID
1 |  |  | LI_BR_01
2 |  |  | LI_BR_02
3 |  |  | LI_BR_03
4 |  |  | LI_BR_04
5 |  |  | LI_BR_05
Group Leader:

## User stories
Application Under Test: | Edureka
Module: | Discover Top Categories
Epic | User story Id | User Story | Acceptance criteria
Epic_01 Discover_Top_Categories | US_ID_1 | As a learner, I want to view the “Discover Top Categories” section on the homepage so that I can see trending course categories. | 1. Homepage should load successfully. 2. “Discover Top Categories” section should be visible without UI issues. 3. Section should display at least 6 categories with names and icons. 4. Section should be responsive on desktop
| US_ID_2 | As a learner, I want to view the “Discover Top Categories” section on the homepage and navigate to Artificial Intelligence, Data Science, and Cloud Computing pages so that I can explore trending courses. | 1. Clicking Artificial Intelligence navigates to AI course page. 2. Clicking Data Science navigates to Data Science course page. 3. Clicking Cloud Computing navigates to Cloud Computing course page.
| US_ID_3 | As a learner, I want to click on "Post Graduate Program in Generative AI and ML" so that I can "view program " details. | 1. Clicking the program link should open the program details page. 2. Page should display program overview, syllabus, and enrollment options.
| US_ID_4 | As a learner, I want to click on Download Brochure and enter valid data so that I can download the brochure successfully. | 1. Clicking “Download Brochure” should open a form. 2. Form should validate required fields (name, email, phone). 3. After valid submission, brochure should download successfully. 4. Confirmation message should appear after download.

## Test Scenario
Application Under Test: |  |  | Edureka
Test Scenario
S.No | Module | Test Requirement Id | Test Scenario Id | Test Scenario Description
1 | Discover Top Categories | TR_01 | TS_1 | To verify that the homepage displays the “Discover Top Categories” section with at least 6 categories.
2 | Discover Top Categories | TR_02 | TS_2 | To verify and apply for "PG Programs"
3 | Discover Top Categories | TR_03 | TS_3 | To verify navigation to Data Science category page from the homepage and applying filters "Career path" to select the course
4 | Discover Top Categories | TR_04 | TS_4 | To verify navigation to Cloud Computing category page from the homepage.
5 | Discover Top Categories | TR_05 | TS_5 | To verify navigation to Post Graduate Program in Generative AI and ML page and successful brochure download after valid data entry.

## Test Cases
| Application Under Test: | Edureka
TS_ID | TC_ID | Objective | Pre condition | Steps | Test Data | Expected Result | Post condition | Test Type | Actual Result | Status | Remark/Comment
TS_1 | TC_01 | Verify homepage loads successfully | Browser should be launched | Open Edureka homepage | URL: https://www.edureka.co | Homepage loads without errors | Homepage ready for interaction | Functional Testing | Homepage displayed | Passed
| TC_02 | Verify scrolling to “Discover Top Categories” section | HomePage is loaded | Scroll down | NA | Section visible | Section displayed | Functional Testing | Section visible | Passed
| TC_03 | Verify section displays at least 6 categories | HomePage is loaded | Count categories | NA | Minimum 6 categories displayed | Categories displayed | Functional Testing | 6 categories visible | Passed
TS_2 | TC_04 | Verify navigation to PG Programs page | HomePage is loaded | Click “PG Programs” | NA | Redirects to PG Programs page | PG Programs page loaded | Functional Testing | Page displayed | Passed
| TC_05 | Verify PG Programs page content | HomePage is loaded | Check program details | NA | Details displayed correctly | Program page loaded | Functional Testing | Details correct | Passed
TS_3 | TC_06 | Verify navigation to Data Science page | PG Programs page loaded | Click “Data Science” | NA | Redirects to Data Science page | Data Science page loaded | Functional Testing | Page displayed | Passed
| TC_07 | Verify applying filter “Career Path” | Homepage loaded | Apply filter | Data Analyst | Filter applied and results updated | Filter applied | Functional Testing | Filter works | Passed
| TC_08 | Verify Data Science courses display | Data Science page loaded | Check course list | NA | Relevant courses displayed | Courses visible | Functional Testing | Courses displayed | Passed
TS_4 | TC_09 | Verify navigation to Cloud Computing page | Filter applied | Click “Cloud Computing” | NA | Redirects to Cloud Computing page | Cloud page loaded | Functional Testing | Page displayed | Passed
| TC_10 | Verify Cloud Computing courses display | Homepage loaded | Check course list | NA | Relevant courses displayed | Courses visible | Functional Testing | Courses displayed | Passed
TS_5 | TC_11 | Verify navigation to Post Graduate Program page | Post Graduate program page is displayed | Click program link | NA | Program details page opens | Program page loaded | Functional Testing | Page displayed | Passed
| TC_12 | Verify Download Brochure button | Program page loaded | Click “Download Brochure” | NA | Form opens | Form displayed | Functional Testing | Form visible | Passed
| TC_12 | Verify form validation with invalid email | Form loaded | 1. Enter invalid email 2. Submit | Email: abc | Error message displayed | Form remains | Functional Testing | Error displayed | Passed
| TC_13 | Enter only 9 digits in phone field and submit | Form loaded | 1. Enter 9 digits in phone field 2. Submit | Phone: 987654321 | Error message not displayed | Form remains | Functional Testing | No error message | Failed
| TC_14 | Enter with invalid data | Form loaded | 1. Enter invalid name, email, phone 2. Submit | Name: Joh57181 Email: john@ Phone: 98765432 | Error message displayed | Form remains | Functional Testing | Error message is displayed | Passed
| TC_15 | Enter with valid data | Form loaded | 1. Enter valid name, email, phone 2. Submit | Name: John Email: john@test.com Phone: 9876543210 | Brochure is downloaded | Brochure downloaded | Functional Testing | Brochure Downloaded | Passed

## Defect Report
Defect Id. | Summary | Module Name | Description | Steps to reproduce | Priority | Severity | Reported By | Reported On | Assigned To | Status | Environment
DF_Discover_Top_Categories_01 | No error for invalid phone number | Discover_Top_Categories | Brochure download form accepts phone number with only 9 digits | 1. Navigate to Edureka homepage 2. Scroll to Discover Top Categories 3. Click “Post Graduate Program in Generative AI and ML” 4. Click “Download Brochure” 5. Enter phone number with 9 digits 6. Submit form | High | High | abc@gmail.com | 2025-11-06 | xyz@gmail.com | New | Chrome

## RTM
Application Under Test: Edureka
Requirement Traceability Matrix
BR_ID | TR_ID | TS_ID | TC_ID | Status | Defect_Id
BR_01 | TR_01 | TS_01 | TC_01 | Passed | NA
|  |  | TC_02 | Passed | NA
|  |  | TC_03 | Passed | NA
| TR_02 | TS_02 | TC_04 | Passed | NA
|  |  | TC_05 | Passed | NA
| TR_03 | TS_03 | TC_06 | Passed | NA
|  |  | TC_07 | Passed | NA
|  |  | TC_08 | Passed | NA
| TR_04 | TS_04 | TC_09 | Passed | NA
|  |  | TC_10 | Passed | NA
| TR_05 | TS_05 | TC_11 | Passed | NA
|  |  | TC_12 | Passed | NA
|  |  | TC_13 | Failed | DF_Discover_Top_Categories_01
|  |  | TC_14 | Passed | NA
|  |  | TC_15 | Passed | NA

## Test Execution summary
TEST EXECUTION SUMMARY
Project Name | Test Scenario | Total Test Cases | Total Test Cases Executed | Total Test CasesPassed | Total Test CasesFailed | Pass Percentage | Fail Percentage | Complition Percentage
Edureka Discove_Top_Categories | To verify navigation to Post Graduate Program in Generative AI and ML page and successful brochure download after valid data entry. | 15 | 15 | 14 | 1 | 93.33% | 6.67% | 100%

## Summary
Test Summary Report format
1. Test Objective: | This document captures the activities performed as part of testing the “Discover Top Categories” module of the Edureka application.
2. Application Overview: | The Discover Top Categories section on Edureka’s homepage allows users to explore various course categories, navigate to category and subcategory pages, and download brochures for specific programs. It ensures smooth navigation and accurate display of categories for an enhanced user experience.
3. Testing Scope:
In-Scope: | Homepage display of “Discover Top Categories” Navigation to category and subcategory pages Navigation to program details page Brochure download functionality
Out of Scope: | Premium programs and subscription features
Areas Not Covered: | Payment gateway Course enrollment process User profile settings
4. Test Metrics
Metric | Count
Total number of test cases planned | 15
Total number of test cases executed | 15
Total number of test cases passed | 14
Total number of test cases failed | 1
Remark:
All test steps were executed successfully except one failure in phone number validation.
Details:
Passed: 14
Failed: 1
Blocked: 0
Requirement Traceability Matrix
BR_ID | TR_ID | TS_ID | TC_ID | Status | Defect ID
ED_BR_01 | TR_01 | TS_1 | TC_01 | Passed
ED_BR_02 | TR_02 | TS_2 | TC_02 | Passed
ED_BR_03 | TR_03 | TS_3 | TC_03 | Passed
ED_BR_04 | TR_04 | TS_4 | TC_04 | Passed
ED_BR_05 | TR_05 | TS_5 | TC_05 | Failed | DF_Discover_Top_Categories_01
5. Types of Testing Performed
Functional Testing - | Verified navigation and display of categories.
UI Testing – | Checked layout and responsiveness of category section.
Integration Testing – | Ensured smooth transition between homepage and category pages.
Usability Testing – | Confirmed intuitive navigation for end users.
6. Test Environment and Tools Us
Application URL: | https://www.edureka.co
Database: | NA
Tools Used: | MS Excel, Jira for defect tracking
7. Recommendations and Suggestions
Improve error handling for brochure download failures.
Optimize category page loading time for better user experience.
8. Exit Criteria
All planned test cases executed.
No critical defects impacting core functionality.
All identified issues documented for resolution.
9. Sign-Off
Considering the nature of the identified defect as low severity and completion of all planned test cases, the testing team recommends proceeding with the release of the Discover Top Categories module.